## URL
Project Details
Project Name: | Peak 72 Application Admin Panal
Project Start Date: | 02.05.24
Testing Start Date | 24.09.2024
Client Name: | Peak 72
Prepared By: | Ronak Patel
Reference Document
Source Document Link - SRD/BRD:
Figma Link: | https://www.figma.com/design/JUFSaNTTke9gOtnyL3bdFg/PEAK-72-Admin-Panel?node-id=218-1353&t=mHEYIIwD5JnGBu1y-1
Website link for testing : | https://admin.peak72finance.com/login
Credential
User Name: | popeye@yopmail.com
Password: | Popeye@123

## Scenarios
Sr. No. | Test Scenarios | Pages | Sub Pages
1 | Login Page |  | Sign In
2 | Logout Page |  | Not available
3 | Dashboard-Home |  | Remaining
4 | Management | Catalogue | Brand
Category
Skill
Question
Quiz
Glossary
|  | Content | Pages
Template
Orders
Shipment
Product
Feedback
|  | User | Administrator
Application User
5 | Settings | My Profile
Company
Address
1 | Bug Summary report |  | Bug Summary Report

## Login
DATE OF CREATION | 24.09.24 |  |  |  | TOTAL PASS | 12
MODULE NAME | Login |  |  |  | TOTAL FAIL | 4
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 16
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Screenshot | Design Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
Login | Verify UI |  |  |  |  | Pass
| Verify the title used like: Email Address / Password |  |  |  |  | Pass
| Verify Eye button |  |  | When we click on eye button, the password should be shown. And when we clicked on the crossed eye button, the password should be unreadable | Here the Eye button work reverse | Pass | [5 empty] | same as twitter(x) | Done 18.10.24
| Forgot password work |  |  |  |  | Pass
| Verify the remember me button-when user click on the remember me button, user can login without entering Email Address / Password |  |  |  |  | Pass
| Verify forgot password button work - It will be redirected on the email id pop up after adding email id, message will be sent on email address and user should get link for reset the password. | 1) Click on Forgot Password 2) Enter Email Address 3) Click on continue button |  |  |  | Pass
| Verify - Eye button on New password and Confirm Password |  |  | When we click on eye button, the password should be shown. And when we clicked on the crossed eye button, the password should be unreadable | Here the Eye button work reverse | Pass | [5 empty] | same as above | Done 18.10.24
| Verify Reset password - New Password and Confirm password both should be same |  |  |  |  | Pass
| Verify Reset password - New Password and Confirm password both are not same |  |  | Passwords does not match |  | Pass
| Verify - Password change-Back to login button work |  |  |  |  | Pass
| Sign in with google option is not available, Pls refer figma |  |  |  |  | Fail | [5 empty] | admin can not register/login with google | Not required
| The sentence "Welcome Back! User" is incorrect for a first-time login user. So, Text should be "Welcome User" |  |  | Welcome User | Welcome Back! User | Pass | [5 empty] | done | Done 18.10.24

## Sign Up (hidden)
DATE OF CREATION | 24.04.24 |  |  |  | TOTAL PASS
MODULE NAME | Sign Up |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 0
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Screenshot | Design Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
Pass
| Verify the all field |  |  |  |  | Fail
Verify User and Email both are allow to enter
Verify valid Email Id
Verify Invalid Email Id
Verify Phone number - only allow 10 digits
Verify Phone number - Character and Special character not allow - Also Space is not allowed-Strict validation would be given
Verify Birthdate format-it should be DD/MM/YYYY or MM/DD/YYYY-Any one of them
Verify Password - Eye button - Open - able to see password
Verify Password - Eye button - Close - not able to see password and come with *****
Verify Confirm Password - Eye button - Open - Able to see password
Verify Confirm Password - Eye button - Close - Not able to see password and come with *****
Verify - Have a referral code - Functionality should be work properly
Verify Referral code popup functionality
Verify Continue / back button work
Verify Enable Location button work
Verify Not now button work
Verify Enable your notification button work
Verify Enable Location / Not Now button work
Verify Apply button functionality
Verify Agree with terms and condition
Verify link should be redirect when we lick on Terms os Service and Privacy Policy
Verify UI Design of form
Verify create account functionality
Verify If you have already account then user should be able to login
Verify all the validation message
Verify all the spelling of word used in the form

## Home-Dashboard
DATE OF CREATION | 24.04.24 |  |  |  | TOTAL PASS
MODULE NAME | Home Page |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 0
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Actual Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment

## Catalogue-Brand
DATE OF CREATION | 24.09.24 |  |  |  |  | TOTAL PASS | 15
MODULE NAME | Catalogue-->Brand |  |  |  |  | TOTAL FAIL | 7
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 22
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
24.09.24 | Brand | Verify Path-It seems wrong |  |  | It should be Dashboard / Catalogue / Brand Management | It displays like Dashboard/Brand Management | Pass
|  | Verify title-"Brands Management" |  |  | It should be "Brand Management" | "Brands Management" Correct phase should be "Brand Management" However we can use it but seems odd. | Pass | [5 empty] | done | Done 18.10.24
|  | Verify search button functionality |  |  |  |  | Pass
|  | Verify Sort(Filter) button functionality i.e Newest and oldest |  |  |  |  | Pass
|  | "All" button should be available in the newest and oldest filter so that admin can able to view all brands |  |  |  |  | Pass | [5 empty] | we can't add all button in sorting | No need to do 18.10.24
|  | Verify UI of sort |  |  |  |  | Pass
| Add Brand | Verify Add functionality | 1) Logged In 2) Click On Catalogue 3) Click on Brand 4) Click on Add brand 5) Enter Brand 6) Click on submit | Test | Brand Added successfully |  | Pass
|  | Verify Title like "Name" It should be "Brand Name" |  |  |  |  | Pass | [5 empty] | done | Done 18.10.24
|  | Verify validation message like "Name should not be empty" |  |  | Brand Name should not be empty | Name should not be empty. It should be "Brand name should not be empty" | Pass
|  | Verify validation message like "Brand added successfully" |  |  |  |  | Pass
|  | Verify View button functionality |  |  |  |  | Pass
|  | Verify Image size-Image size is different so, it looks weird |  |  | Image size should be fixed |  | Pass | [5 empty] | done | Done 18.10.24
|  | Verify UI of text box text |  |  |  | When we enter a long text, some text comes in second line. so we should set some characters limit after increasing it should be shown like below: Anirudhsdasdsss….. When user click on view then they can able to see the full text | Pass | [5 empty] | done | Done 18.10.24
|  | Verify Duplication - it should not be allowed duplicate brand |  |  |  |  | Pass
| EditBrand | Verify update brand details | 1) Logged In 2) Click On Catalogue 3) Click on Brand 4) Click on View Button 5) Click on Edit brand 6) Type name which u want to edit 7) Add Icon 8) Click on submit |  | 1) "Brand details updated successfully" 2) "Invalid file type". | At the time of update brandname, "Add Icon" should be added compulsory. And message comes like "Invalid file type". Validation message should be different like "Please add icon" or else. At the time of "Add Brand", icon add is not compulsory Pls do the same in both refer video | Pass
|  | Verify update Icon |  |  |  |  | Pass
| Delete Brand | Verify delete button functionality | 1) Logged In 2) Click On Catalogue 3) Click on Brand 4) Select any one brand 5) Click on delete button 6) Yes, Delete it 7) Click on submit |  | Brand remove successfully |  | Pass
|  | Verify validation message of delete brand |  |  | Msg should be like "Are you sure about removing 'brand name'? " Same like below : Are you sure about deleting Jotun? | Message comes like "Are you sure about removing Peak?" | Pass
| View Brand | Verify view button functionality |  |  |  |  | Pass
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | One text coming beside the filter of row |  |  |  | Sentence/text comes like "Showing NaN to NaN of undefined entries" | Pass | [5 empty] | done | Done 18.10.24
| Page filter | Verify the page filter Check previous and next button work |  |  | Pagewise filter should be came | After adding 12 rows, I have filter row by 6 . Data comes in only one page with 6 brand. Other remaining brand should be came in second page but here only one page comes | Pass | [5 empty] | done | Done 18.10.24

## Catalogue-Category
DATE OF CREATION | 24.09.24 |  |  |  |  | TOTAL PASS | 15
MODULE NAME | Catalogue-Category |  |  |  |  | TOTAL FAIL | 6
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 21
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bugs | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
25.09.24 | Category | Verify Path |  |  | Dashboard/Category Management | Path should be Dashboard/Catalogue/Category Management | Pass | [6 empty] | Done 18.10.24
|  | Verify sorting-Oldest/Newest functionality |  |  |  |  | Pass
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [6 empty] | No need to do 18.10.24
|  | Verify the text of sorting |  |  |  |  | Pass
|  | Verify UI of header like Sort/Category Types/Searchbar |  |  |  |  | Pass
|  | Verify sorting by "Category Type" dropbox functionality All Skill Product |  |  |  |  | Pass
|  | Verify search button functionality |  |  |  |  | Pass
|  | Verify UI of text box text |  |  |  | When we enter a long text, some text comes in second line. so we should set some characters limit after increasing it should be shown like below: Anirudhsdasdsss….. When user click on text box then they can able to see the full text | Pass | [6 empty] | Done 18.10.24
| Add Category | Verify add functionality |  |  |  |  | Pass
|  | Verify validation message when we add category |  |  | "Category Added successfully" | Same like expected result | Pass
|  | When image is blank at that time one dummy image should be came |  |  |  |  | Pass | [6 empty] | Done 18.10.24
|  | Verify text of header like sort/category types |  |  | Category type display like below : Skills Product | Here it displays like : Skills Product It should be like : Skills Products | Pass | [6 empty] | Done 18.10.24
|  | Verify First letter should be capital in Add category |  |  |  |  | Pass
|  | Veri type button dropdown text and its work |  |  |  |  | Pass
|  | Verify "Created At" and "Created by" comes correct |  |  |  |  | Pass
|  | Verify Duplication - it should not be allowed duplicate category |  |  |  | Category already exists | Pass
| Edit Category | Verify update category details | 1) Logged In 2) Click On Catalogue 3) Click on Category 4) Click on View Button 5) Click on Edit Category 6) Type name which u want to edit 7) Add Icon 6) Click on submit |  | Category details updated successfully | At the time of update category, Add icon should be added compulsory. And messaage comes like "Invalid file type". Validation message should be different like "Please add icon" or else. At the time of "add category", icon add is not compulsory Pls do the same in both refer video | Pass | [6 empty] | Done 18.10.24
|  | After selecting the image, image should be comes no need to refresh it when we edit/Add |  |  |  |  | Fail | [6 empty] | Will do later
| Delete Category | Verify delete category functionality | 1) Logged In 2) Click On Catalogue 3) Click on Category 4) Select any one category 5) Click on delete button 6) Yes, Delete it 7) Click on submit |  | Category removed successfully |  | Pass
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page filter | Verify the page filter Check previous and next button work |  |  | Pagewise filter should be came | After adding 12 rows, I have filter row by 6 . Data comes in only one page with 6 category. Other remaining category should be came in second page but here only one page comes | Pass | [5 empty] | done | Done 18.10.24

## Catalogue-Skill
DATE OF CREATION | 26.09.24 |  |  |  |  | TOTAL PASS | 18
MODULE NAME | Catalogue-Skill |  |  |  |  | TOTAL FAIL | 8
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 26
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
26.09.24 | Skill Management | Verify Path |  |  | Dashboard /Skills Management | Path should be Dashboard/Catalogue/Skill Management | Pass | [5 empty] | done | Done 18.10.24
|  | Verify sorting-Oldest/Newest functionality |  |  |  |  | Pass
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [5 empty] | in sorting list order, we ain't use "all". | Done 18.10.24
|  | Verify the text of sorting |  |  |  |  | Pass
|  | Verify UI of header like Sort/Category types/Searchbar |  |  |  |  | Pass
|  | Verify sorting by "Category Type" dropbox functionality |  |  |  |  | Pass
|  | Verify Search functionality in sorting (Category Type) dropbox |  |  |  |  | Pass
|  | Verify search button functionality |  |  |  |  | Pass
|  | Verify UI of text box -- text view |  |  |  | When we enter a long text, some text comes in second line. so we should set some characters limit after increasing it should be shown like below: Anirudhsdasdsss….. When user click on view then they can able to see the full text Here some texts are cut | Pass | [5 empty] | done | Done 18.10.24
| Add Skill | Verify add functionality | 1) Logged In 2) Click On Catalogue 3) Click on Add Skill Button 4) Click on Edit Category 5) Enter Skill name and Select Category 6) Add Icon 7) Click on For premium user button 8) Click on submit |  | Skill added Successfully | Skill added Successfully | Pass
|  | Verify for Premium user toggle |  |  |  |  | Pass
|  | Verify validation message when we add category |  |  | Skill added Successfully | Same like expected | Pass
|  | Verify Image icon upload successfully |  |  |  |  | Pass
|  | Verify text of header like sort/category |  |  |  |  | Pass
|  | Verify First letter should be capital in Skill Name and category type |  |  |  |  | Pass
|  | Verify type button dropdown text and its work |  |  |  |  | Pass
|  | Verify "Created At" and "Created By" comes correct |  |  |  |  | Pass
|  | Verify Duplication - it should not be allowed duplicate Skill at the time of add Skill |  |  |  | Category already exists | Pass
|  | Image size should be same for all image |  |  |  |  | Pass | [5 empty] | done | Done 18.10.24
| Edit Skill | Verify update Skill | 1) Logged In 2) Click On Catalogue 3) Click on Skill 4) Click on View Button 5) Click on Edit Skill 6) Type name which u want to edit 7) Add Icon 8) Click on submit |  | Skill details updated successfully | 1) At the time of update category, Add icon should be added compulsory. And messaage comes like "Invalid file type". Validation message should be changed like "Please add icon" or else. 2) At the time of "add category", icon add is not compulsory Pls do the same in both refer video | Pass | [5 empty] | done | Done 18.10.24
|  | When We edit any Skill name with same skill name and same category, it is allowed to be editing. And message comes like "Skill details updated successfully" |  |  | Duplicate record should not allowed to be edited |  | Pass | [6 empty] | Done 18.10.24
|  | After selecting the image for upload, image should be comes no need to refresh it, when we edit/Add in the edit page |  |  |  |  | Fail | [5 empty] | done | Need to do later
| Delete Skill | Verify validation message | 1) Logged In 2) Click On Catalogue 3) Click on Skill 4) Select any one Skill 5) Click on delete button 6) Yes, Delete it 7) Click on submit |  | It should be "Skill removed successfully" | Category removed successfully | Pass | [5 empty] | done | Done 18.10.24
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass
| For premium user | Button should be small than current

## Catalogue-Question
DATE OF CREATION | 26.09.24 |  |  |  |  | TOTAL PASS | 28
MODULE NAME | Question Management |  |  |  |  | TOTAL FAIL | 10
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 38
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bugs | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
26.09.24 | Question Management | Verify Path |  |  | Dashboard /Question management | Path should be Dashboard/Catalogue/Question management | Pass | [6 empty] | Done 17.10.24
26.09.24 |  | Verify sorting-Oldest/Newest functionality |  |  |  |  | Pass
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [6 empty] | Done 17.10.24
|  | Verify the text of sorting |  |  |  |  | Pass
|  | Verify UI of header like Sort/Select Type/Select Level/Searchbar |  |  |  |  | Pass
|  | Verify sorting by "Select Type" dropbox functionality option like : Short Answer/Multiple choice/Check box/Dropdown |  |  |  |  | Pass
|  | Verify Select Level like : Easy / Medium / Hard/ Expert / Master / Extreme |  |  |  |  | Pass
|  | Verify search button functionality |  |  |  |  | Pass
|  | Verify title like Question/Level/Type/Created At/Action |  |  |  |  | Pass
|  | Verify UI of question management |  |  |  | All list of questions should be in left align. so, it will look decent. | Pass | [6 empty] | Done 17.10.24
| Add Question | Verify title like Question title/Question Description/Question Type/Question Level/Answer Type/Answer Points/Duration/Answer Value/Answer Description/Answer Hit |  |  |  |  | Pass
|  | Verify - First letter should be capital in title |  |  |  |  | Pass | [6 empty] | Done 17.10.24
|  | Verify - First letter should be capital in question Title / description /Add option(Option 1 and other when we select multi question) and answer value |  |  |  | However it comes in capital letter (first letter) | Pass | [6 empty] | Done 17.10.24
|  | Verify validation message |  |  |  |  | Pass
|  | Verify validation message of question title |  |  |  | Question title is required | Pass
|  | Verify Answer Type (Single-Valued/Multi-Valued) |  |  |  |  | Remaining
|  | Verify - Answer points - Characters and Special characters should not be allowed |  |  |  |  | Pass
|  | Verify - Answer points - digit limits |  | 1.0423e+45 |  | Here it is allowed 1042342343423423123123123122333333333333333333 We should set the digit limit | Pass | [6 empty] | Done 17.10.24
|  | Verify validation message |  |  |  | Points are required | Pass
|  | Verify - Duration - Characters and Special characters should not be allowed |  |  |  |  | Pass
|  | Verify duration - limit of digit to be allowed |  | 7.6768e+38 |  | (1440 minutes for a 24-hour period so , we should not given more than that of, Here it allows digit like 767676767676767676767876876876876876876 We should set the digit limit of minutes for giving the answer. We have to ask to the client about this limit, else we have to decide. Strict validation should be there for not allowing more than fixed digit | Pass | [6 empty] | Done 17.10.24
|  | Verify - Duration-Validation message |  |  |  | Duration is required | Pass
|  | Verify "Add more" button functionality |  |  |  |  | Pass
|  | Verify "options" should be deleted by delete button |  |  |  |  | Pass
|  | Verify "Answer Value" - Validation message |  |  |  | "Answer value is required" | Pass
|  | Verify Special characters should not be allowed in Answer value But in some answer we have to allow so we have to keep as it is. Example Question: What symbol is used to represent multiplication in programming languages like Python or Java? Answer: * (asterisk) |  |  |  |  | Pass | [6 empty] | Need to discuss with client
|  | Verify Answer hit |  |  |  | Not reflacted Not working | Fail | [6 empty] | Will do later
|  | Verify Question level contents like Easy / Medium / Hard / Expert / Master / Extream |  |  | Easy Medium Hard Expert Master Extream | Same as expected | Pass
|  | Verify Answer value Character limit - When we select single answer at that time, it should no any character limit in "Answer value" But validation should be there like "You have to enter something" and also set this in App view |  |  | It allowing to enter answer | I have added one question in the Admin Panel and the Answer Value has been set as "No" in "short question" (question type). However, in the App View, users are required to input a minimum of 5 characters which is set as a validation. If the answer is shorter than 5 characters (e.g., "No"), then it is not allowed to be submit | Fail | [6 empty] | Tanmay will do
| View Button Functionality | Verify View button functionality |  |  |  |  | Pass
| Update Button Functionality | Verify update button functionality |  |  | Details updated and message should be came like : "Question details updated successfully" | Same as expected | Pass
|  | Verify - duplicate question - It should not allowed to be entered at the time of edit/update |  |  | Should not be allowed dulpicate question to be entered and message should be cames like : Question already exists | Same as expected | Pass
| Abort Button Functionality | Verify Abort button functionality work |  |  |  |  | Pass
| Cancel Button Functionality | Verify Cancel button functionality work |  |  |  |  | Pass
| Delete Button Functionality | Verify delete button functionality work | 1) Logged In 2) Click On Catalogue 3) Click on Question 4) Select any one category 5) Click on delete button 6) Yes, Delete it 6) Click on submit |  | Question removed successfully | Same as expected | Pass
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass
| Select all | Verify after click on select all item and delete all , all selected record should be deleted. And validation message comes. | 1) Logged In 2) Click On Catalogue 3) Click on Question 4) Click on select all button 5) Click on "Delete All" button 5) Click on "Yes Delete" button |  | Validation message should be "Questions removed successfully" | Question removed successfully | Fail | [6 empty] | Backend
|  | Verify Counting of marks |  |  |  |  | Remaining

## Catalogue-Glossary
DATE OF CREATION | 27.09.24 |  |  |  |  | TOTAL PASS | 18
MODULE NAME | Glossary |  |  |  |  | TOTAL FAIL | 7
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 25
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Actual Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bugs | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
27.09.24 | Quiz Management | Verify Path |  |  | Dashboard / Glossary Management | Path should be Dashboard/Catalogue/Glossary Management | Pass | [5 empty] | done | Done 18.10.24
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [5 empty] | we can't add all button in sorting | No need to do it
|  | Verify the sort filter functionality |  |  |  |  | Pass
|  | Verify the search bar functionality |  | ABC |  |  | Pass
|  | Verify if item not available and search it, Data should not be searched |  |  | No Results found | As per expected result | Pass
|  | Verify UI of Glossary Management |  |  |  |  | Pass
|  | Verify title like Glossary / Slug / Created By / Created At / Action |  |  |  |  | Pass
| Add Glossary | Verify Add glossary successfully | 1) Logged In 2) Click On Catalogue 3) Click on Glossary 4) Click on Add Glossary 5) Type name which u want to add and add description 6) Click on submit |  |  |  | Pass
|  | Verify - First letter of the title should be came in capital at the time of entering title |  |  |  |  | Pass
|  | Verify - First letter of the description should be came in capital at the time of entering description |  |  |  |  | Pass | [5 empty] | done | Done 18.10.24
|  | Verify validation message for name and description |  |  |  | Name must be at least 3 characters long Description should not be empty Glossary name is required | Pass
|  | Verify punctuation mark (special characters)should be allowed in description |  | Title:Heven Description : the place where, in some religions, it is believed that God lives and where good people go when they die | Punctuation mark should be allowed. | Here, I have added below glossary with punctuation mark, but with the punctuation mark did not allow to entered. - Title : Heven Description : the place where, in some religions, it is believed that God lives and where good people go when they die. | Pass | [5 empty] | Done | Done 18.10.24
|  | Verify validation message for Name |  |  | Glossary name is required | Same as expected result | Pass
|  | Verify validation message for Description |  |  | It should be "Description must be less than 150 characters | Description must be less then 150 characters | Pass | [5 empty] | done | Done 18.10.24
|  | Verify duplication should not be allowed |  |  | Glossary already exists. |  | Pass
| View button functionality | Verify view button functionality |  |  |  |  | Pass
| Update button functionality | Verify Edit button functionality | 1) Logged In 2) Click On Catalogue 3) Click on Glossary 4) Click on View button which u want to edit Glossary 5) Click on Edit glossary 6) Edit content 7) Click on Submit |  | Glossary details updated successfully | Same as per expected result | Pass
|  | Verify Edit button functionality glitch occur |  |  | Name and description should be came when we edit any glossary | When we edit any glossary at that time details comes like "Name" and "Description" But here details are not comes | Pass | [5 empty] | done | Done 18.10.24
| Delete button functionality | Verify delete glossary button functionality | 1) Logged In 2) Click On Catalogue 3) Click on Glossary 4) Click on delete button which u want to delete Glossary 5) Click on "Yes Delete" button |  | Glossary removed successfully | Same as expected result | Pass
|  | When we deleted glossary , successful deletion message should be came |  |  |  | Here no any message comes | Pass | [5 empty] | done | Done 18.10.24
| Rows Filter | Verify filter of the row i.e 5/10/15…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass
| Select all | Verify after click on select all item and delete all , all selected record should be deleted | 1) Logged In 2) Click On Catalogue 3) Click on Glossary 4) Click on select all button 5) Click on "Delete All" button 6) Click on "Yes Delete" button |  |  |  | Pass
|  | Verify "No, Cancel" button work |  |  | Glossary removed successfully |  | Pass
|  | Verify UI of successful message after adding glossary |  |  |  | Message - "Glossary details updated successfully. It comes in small box at the top right side. | Pass | [5 empty] | done | Done 18.10.24

## Catalogue-Quiz
DATE OF CREATION | 26.09.24 & 27.09.24 |  |  |  |  | TOTAL PASS | 18
MODULE NAME | Quiz Management |  |  |  |  | TOTAL FAIL | 10
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 28
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bugs | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
26.09.24 | Quiz Management | Verify Path |  |  | Dashboard / Quiz Management | Path should be Dashboard/Catalogue/Quiz Management | Pass | [5 empty] | done | Done 17.10.24
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [5 empty] | in sorting list order, we ain't use "all". | No need to do
|  | Verify the sort filter functionality |  |  |  |  | Pass
|  | Verify the search bar functionality |  | ABC |  |  | Pass
|  | Verify if item not available and search it, Data should not be searched |  | WERT | No Results found | As per expected result | Pass
|  | Verify title like Quiz/Slug/Created By/Created At/Action |  |  | One more column shoud be there for image at "first" or after "created at" So that in view of Quiz management , admin can easily see it. |  | Fail | [6 empty] | No need to do dev said
| Add Quiz | Verify Quiz level contents like Easy / Medium / Hard / Expert / Master / Extream |  |  | Level 1 Level 2 Level 3 Level 5 Level 6 | In App view, it display Level 1/Level 2/Level 3/Level 4/Level 5/Level 6 So, we should keep level 1.2.3.4,5,6 in place of Easy/ Medium/ Hard/ Expert/Master/Extream in admin panal. So, that user can understand | Fail | [6 empty] | will do it later
|  | Verify all title like Quiz Title/Quiz Type/Quiz Level/In which skill/Add Pre Description-Title/Description |  |  |  |  | Pass
|  | Verify validation message of Quiz title |  |  |  | Quiz title is required | Pass
|  | Verify "Quiz Type" dropbox like Skill/Survey |  |  |  |  | Pass
|  | Verify First letter of the quiz title should be came in capital Also do in description and Title |  | account |  | However, data displayed with first letter capital | Pass | [5 empty] | done | Done 17.10.24
|  | Verify after click on survey or skill, quiz comes under their types |  |  |  |  | Pass
|  | Verify title of Quiz has limitation of characters to be entered because it is effected on app home screen title |  |  | Pls refer screenshot |  | Pass | [6 empty] | Done 17.10.24
|  | Quiz level given in "Question" and "Quiz" in both that create the confusion. |  |  |  | I have created one question like "Automation is more useful than manual" and In the question management I had to select level like " Easy". When I went for quiz management again Quiz level option came for selection . | Fail | [5 empty] | done
|  | Verify Quiz level title like Easy / Medium / Hard / Expert / Master / Extream |  |  | Title of Quiz level should be as below : Level 1 Level 2 Level 3 Level 4 Level 5 Level 6 | Quiz level comes as below: Easy Medium Hard Expert Master Extream | Fail
| View Quiz | Verify View button functionality |  |  |  |  | Pass
|  | Verify selected question at below in quiz Title should be start in left align for the UI percepective |  |  |  |  | Pass | [5 empty] | done | Done 17.10.24
| Question list | Verify search box button functionality when we select question in question list in quiz |  |  |  |  | Pass
|  | Verify select type drop box functionality in question list in quiz |  |  |  |  | Pass
|  | Verify dropbox functionality "select level" in question list in quiz |  |  |  |  | Pass
|  | Verify - After "Selecting Level" and "Select Type" - selecting multiple question from the list |  |  |  |  | Pass
|  | Verify "Insert Selected Questions" button functionality |  |  |  |  | Pass
|  | Verify a text comes on top in question list like - Question List (4 selected) |  |  | After selecting more and more , value should be changed |  | Pass
|  | Verify UI - Image in left side design looks not good If possible then please arrange it on right side So the below text comes in one side |  |  |  |  | Fail | [6 empty] | will do it later
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass
| Select all | Verify after click on select all item and delete all, all selected record should be deleted | 1) Logged In 2) Click On Catalogue 3) Click on Quiz 4) Click on select all button 5) Click on "Delete All" button 5) Click on "Yes Delete" button |  | Quiz removed successfully | As per expected result | Pass
|  | When we update data , no data found comes |  |  |  |  | Pass | [6 empty] | Done 17.10.24

## Retest Bug Summary Report
TEST RESULT SUMMARY REPORT
Module Name | Total Passed | After Resolved Bugs Pass | Total Failed | Remaining to Check | Total Cases
Login Page | 12 | 3 | 1 | 0 | 13
Catalogue Brand | 15 | 7 | 0 | 0 | 15
Catalogue Category | 15 | 7 | 1 | 0 | 16
Catalogue Skill | 18 | 7 | 1 | 0 | 19
Catalogue Question | 28 | 8 | 3 | 0 | 31
Catalogue Quiz | 18 | 6 | 5 | 0 | 23
Catalogue Glossary | 18 | 8 | 0 | 0 | 18
Content Page | 12 | 5 | 0 | 0 | 12
Content Template | 15 | 3 | 2 | 0 | 17
Content Feedback | 4 | 3 | 1 | 0 | 5
Product | 16 |  |  |  | 18
Profile | 18 |  |  |  | 18
Company | 1 |  |  |  | 1
Address | 5 | 9 | 2 | 0 | #REF!
User | 25 |  |  |  | 25
| 0 |  |  |  | 0
Total | 220 |  |  |  | #REF!

## Bug Summary Report
TEST RESULT SUMMARY REPORT
Module Name | Total Passed | Total Failed | Total Cases
Login Page | 12 | 4 | 16
Catalogue Brand | 15 | 7 | 22
Catalogue Category | 15 | 6 | 21
Catalogue Skill | 18 | 8 | 26
Catalogue Question | 28 | 10 | 38
Catalogue Quiz | 18 | 10 | 28
Catalogue Glossary | 18 | 7 | 25
Content Page | 12 | 4 | 16
Content Template | 15 | 6 | 21
Content Feedback | 4 | 4 | 8
Product | 16 | 15 | 31
Profile | 18 | 8 | 26
Company | 1 | 7 | 8
Address | 5 | 11 | 16
User | 25 | 14 | 39
| 0 | #REF! | #REF!
Total | 220 | #REF! | #REF!

## Content-Pages
DATE OF CREATION | 27.09.24 |  |  |  |  | TOTAL PASS | 12
MODULE NAME | Content-Pages |  |  |  |  | TOTAL FAIL | 4
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 16
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bugs | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
27.09.24 | Pages | Verify Path |  |  | Dashboard / Pages | Path should be Dashboard/Content/Pages | Pass | [6 empty] | Done 18.10.24
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [6 empty] | No need to do
|  | Why sort button shape is different than other please do the same in all module |  |  |  |  | Pass | [5 empty] | Done | Done 18.10.24
|  | Verify the sort filter functionality |  |  |  |  | Pass
|  | Verify the search bar functionality |  | Privacy Policy |  |  | Pass
|  | Verify if item not available and search it, Data should not be searched |  |  | No Results found | As per experrcted result | Pass
|  | Verify title like Title/Slug/Created At/Action |  |  |  |  | Pass
| Add Pages | Verify "Add page" button functionality | 1) Logged In 2) Click on Content 3) Click on Page 4) Click on Add Page 5) Enter title and description 6) Click on submit |  | Page added successfully | As per expected result | Pass
| View button Functionality | Verify view button functionality |  |  |  |  | Pass
| Update button Functionality | Verify update button functionality | 1) Logged In 2) Click on Content 3) Click on Page 4) Click on View which you want to edit 5) Click on Update button 6) Edit title and description 7) Click on submit |  | Page details updated successfully | As per expected result | Pass
|  | Verify formate functionality in description work |  |  |  | All function work except link doc | Pass | [5 empty] | Working fine | Done 18.10.24
| Delete button Functionality | Verify delete button functionality | 1) Logged In 2) Click on Content 3) Click on Page 4) Click on delete that you want to delete 5) Click on "Yes, Delete" button functionality |  | Page removed successfully |  | Pass
| Select all | Verify after click on select all item and delete all, all selected record should be deleted | 1) Logged In 2) Click On Content 3) Click on Pages 4) Click on select all button 5) Click on "Delete All" button 6) Click on "Yes Delete" button |  | Page removed successfully | Pages removed successfully | Pass | [6 empty] | Backend
|  | Verify "No, Cancel" button work |  |  |  |  | Pass
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass

## Content-Templates
DATE OF CREATION | 27.09.24 |  |  |  |  | TOTAL PASS | 15
MODULE NAME | Content-Templates |  |  |  |  | TOTAL FAIL | 6
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 21
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Designer Comment | Screenshot | Design Bugs | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
27.09.24 | Template | Verify Path |  |  | Dashboard / Templates | Path should be Dashboard/Content/Template | Pass
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [6 empty] | Done 18.10.24
|  | Verify the Filter functionality |  |  |  |  | Pass
|  | Verify field like All/Email/Message/Notification |  |  |  |  | Pass
|  | Verify the sort button functionality |  |  |  |  | Pass
|  | Verify the search bar functionality |  | Privacy Policy |  |  | Pass
|  | Verify if item not available and search it, Data should not be searched |  |  | No Results found | As per expected result | Pass
|  | Verify title like Title/Slug/Created At/Action |  |  |  |  | Pass
| Add Template | Verify add template functionality |  |  | Template added successfully |  | Pass
|  | Verify title like Title/Type/Description |  |  |  |  | Pass
|  | If the number is not allowed in Title then strict validation should be there for not allowing digit to be entered |  | Dasds324234 | It should allowed to be entered | Please enter a valid name | Pass | [5 empty] | Done | Done 18.10.24
|  | Why shape of filter and sort button different than other, plesae do the same in all module |  |  |  |  | Pass | [5 empty] | Done
|  | Verify "Type" like Email/Message/Notification |  |  |  |  | Pass
|  | Verify duplicate template should not allowed to be entered |  |  |  |  | Pass | [6 empty] | Done 18.10.24
| View Template button functionality | Verify view button functionality |  |  |  |  | Pass
| Delete button functionality | Verify delete button functionality | 1) Logged In 2) Click on Content 3) Click on Template 4) Click on delete that you want to delete 5) Click on "Yes, Delete" button functionality |  | It should be "Templates removed successfully | Template is removed successfully | Fail | [5 empty] | Done | Backend
| Select all | Verify after click on select all item and delete all, all selected record should be deleted | 1) Logged In 2) Click On Content 3) Click on template 4) Click on select all button 5) Click on "Delete All" button 6) Click on "Yes Delete" button |  | Successful message should be came like : Template removed successfully | Template is removed successfully | Fail | [5 empty] | Done | Backend
|  | Verify "No, Cancel" button work |  |  |  |  | Pass
| Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
|  | Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
| Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass

## Feedback
DATE OF CREATION | 27.09.24 |  |  |  |  | TOTAL PASS | 4
MODULE NAME | Content-Feedback |  |  |  |  | TOTAL FAIL | 4
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 8
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Designer Comment | Screenshot | Design | Dev Comments | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
| Feedback | Verify Path |  |  | Dashboard / Feedback |  | Pass
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass |  |  |  |  | it doesn't work with all | No need to do
|  | Why shape of sort button different than other, please do the same in all. |  |  |  |  | Pass |  |  |  |  | Done | Done 18.10.24
|  | Verify search button functionality |  |  |  | Search button functionality not working | Fail |  |  |  |  | from backend
| Add | Verify add feedback | 1) sign in in Application 2) Profile 3) Click on share feedback 4) select emoji 5) Enter text |  | Feedback submitted successfully |  | Pass
| View button functionality | Verify view button functionality |  |  |  |  | Pass
|  | Please modify text "Feedback Detail" to "Feedback Details" and ":" in description field title |  |  | User Name: Ronak Patel Type: Application Rating: ***** Description: It's good | Details comes as below: User Name: Ronak Patel Type: application Rating:***** Description It's good | Pass |  |  |  |  | DOne | Done 18.10.24
| Delete button functionality | Verify delete button functionality | 1) Logged In 2) Click On Content 3) Click on Feedback 4) Click on Delete 5) Click on "Yes Delete it" button 6) Click on "Yes Delete" button |  | Feedback removed successfully | As per expected result | Pass

## Orders (hidden)
DATE OF CREATION | 24.04.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Content-Orders |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Screenshot | Design Bugs | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment

## Shipment (hidden)
DATE OF CREATION | 24.04.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Content-Shipment |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Screenshot | Design Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
24.04.24

## Product
DATE OF CREATION | 27.09.24 |  |  |  |  | TOTAL PASS | 16
MODULE NAME | Content-Product |  |  |  |  | TOTAL FAIL | 15
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 31
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Importance | Screenshot | Design Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
27.09.24 | Product | Verify Path |  |  | Dashboard / Products |  | Pass
|  | One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Pass | [5 empty] | it doesn't work with all | No need to do 21.10.24
|  | Verify the sort filter functionality |  |  |  |  | Pass
|  | Verify the search bar functionality |  | Privacy Policy |  |  | Pass
|  | Verify if item not available and search it, Data should not be searched |  |  | No Results found | As per experrcted result | Pass
| Add Products | Verify "Add Product" button functionality | 1) Logged In 2) Click on Content 3) Click on Product 4) Click on Add Product 5) Enter details 6) Click on submit |  | Product added successfully | As per expected result | Pass
|  | Why only one brand and one category comes at the time of adding product. Please refer screen shot |  |  |  |  | Fail
| Product Information | Verify title of Product Information: Name/Description/Categories/Brand/HSN Code/Manufactured Date/Return Period(in Days) |  |  |  |  | Pass
|  | When we enter worngdate verify validation message |  |  | It should be meaningfull so that geneal user can understand like "You have entered wrong date" | Invalid ISO date string, pls refer screenshot | Pass | [5 empty] | Done | Done 21.10.24
|  | Manufaturing date format should be DD/MM/YYYY Here it is DD/MM/YYYYYY In year 6 digit allowed, However date is not saved |  |  |  |  | Pass | [5 empty] | Done | Done 21.10.24
|  | First letter should be came in capital at the time of entering. |  |  |  |  | Pass | [5 empty] | Done | Done 21.10.24
| Dimensions | Verify title of Dimensions: Weight (in Kg) / Length (in cm) Breadth (in cm) / Height (in cm) |  |  |  |  | Pass
|  | Please give some limitation of digit in Weight (in Kg) / Length (in cm)/Breadth (in cm) / Height (in cm) because it is allowed too much digits pls refer screen recording for the same |  |  |  |  | Fail | [5 empty] | Done
| Country and Currency | Verify title like Country and Currency: Origin Country Select currency Currency Symbol |  |  |  |  | Pass
| Price and Stock | Verify title like Price and Stock: Quantity/Tax type/Tax Value/MRP/Selling Price/Tax included |  |  | It should be as below : Quantity Tax type Tax Value MRP Selling Price Tax Included | Here it is as below : Quantity Tax type Tax Value MRP Selling Price Tax Included Pls update text "Tax Included" | Fail | [5 empty] | Done
|  | Please give some limitation of digits in Quantity/MRP/Selling Price because it is allowed too much digits pls refer screen recording for the same |  |  |  |  | Fail | [5 empty] | Done
|  | Verify only digit should be allowed in Quantity |  |  | Strict validation should be there for not allowing character to be entered | Here validation message comes but why we allow character.? And also For Ui percepective design has been changed when validation message comes. Please refer screen shot | Fail | [5 empty] | max 6 digit limit updated, done
| Shipping | Verify title of Shipping Shipping Charge/Packaging Charge |  |  |  |  | Pass
|  | Please give some limitation of digits in Shipping Charge/Packaging Charge because it is allowed too much digits pls refer screen recording for the same |  |  |  |  | Fail | [5 empty] | max 6 digit limit updated, done
| Specification | Verify Specification: Keys/Value |  |  |  |  | Remaining
|  | When we enter "Key Value" and "Value" it should be came in fist letter capital |  |  |  |  | Fail
|  | Please give some limitation of characters/digits in Key/Value because it is allowed too much digits. Please refer screen recording for the same |  |  |  |  | Fail | [5 empty] | this is upon admin how much he/she want to add
|  | Verify UI-Please set the space as same as others |  |  |  |  | Fail | [5 empty] | Done
|  | Verify delete option functionality |  |  |  |  | Pass
|  | Verify Validation message of Product name |  |  | It should be "Name is required" | name is required | Fail | [5 empty] | Done
|  | Verify Manufactured Date format |  |  | Format should be in dd-mm-yyyy | Here it is allow to be entered date like 03-04-275760 In year only four digit should be allowed. Strictly not allowing to enter more than four digit | Fail
|  | Verify Return period limit |  |  | It should be in two digits | Here, it is allow 34234234234234234237666666666666666666666666666666666666666666666666666666666666666666666666666666666666…. | Fail | [5 empty] | Done
|  | Verify Search button functionality in Origin country |  |  |  |  | Pass
|  | Verify Search button functionality in Select Currency |  |  |  |  | Pass
|  | Verify "Add More" button functionality |  |  |  |  | Pass
|  | Veirfy text of "Add more" |  |  | It should be "Add More" |  | Fail | [5 empty] | Done
| Gallery | Verify upload images |  |  |  |  | Pass
| Update Product | Verify update product details successfully | 1) Logged In 2) Click on Content 3) Click on Product 4) View(Select) anyone product 5) Click on Update 6) Update details 7) Click on submit |  | Product Details updated successful |  | Pass
| Abort | Verify abort button functionality |  |  |  |  | Pass

## Profile
DATE OF CREATION | 30.09.24 |  |  |  |  | TOTAL PASS | 18
MODULE NAME | Setting |  |  |  |  | TOTAL FAIL | 8
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 26
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
30.09.24 | Profile-Account Settings-My Profile | Verify Path |  |  | It should be Dashboard/Setting/Profile | Here it is Dashboard / Profile | Fail
|  | Verify - Change Picture upload functionality |  |  | Picture updated successfully |  | Pass
|  | Verify remove button functionality |  |  |  |  | Pass
|  | Account Settings title Option like Profile/Change Password/Manage Notification/2FA/Deactivate Account |  |  |  |  | Pass
|  | Verify title like First Name/Last Name/Email/Phone Number/Gender/Date of Birth |  |  |  |  | Pass
|  | Verify image upload / change is also comes under update/edit Here I have update image without click on edit button, It is allowed to be update pic |  |  |  |  | Fail | [5 empty] | no need to enable edit to change image
| Edit Profile | Verify update successfully |  |  | User details updated successfully. | Same as Expected result | Pass
|  | Verify phone number should be in 10 digit |  |  |  |  | Pass
|  | Verify characters and special characters should not be allowed in phone number field |  |  |  |  | Pass
|  | Verify Date format |  | 02-02-275760 |  | Here, it is allowed six digits in a year. I have tried to edit date like 02-02-275760, It is allowed to be entered but strict validation should be there. However the validation message comes "You must be 18 years old or above" . Also message shoud be different | Fail
| Discard | Verify Discard button work |  |  |  |  | Pass
|  | Verify email and phone number edit |  |  |  |  | Remaining
|  | Edit detials with the use of edit button |  |  | User details updated successfully |  | Pass
| Email Verification | Verify change email address, verify and sent OTP successful. |  |  | A mail with 6 digit verification code is sent successfully. |  | Pass |  |  |  |  | OTP has been sent to Gmail Acc, but in spam talk with hariom. Also Outlook mail OTP is not sent.
|  | Verify After adding OTP, email id successfully verified |  |  |  |  | Pass
| Phone Verification | Verify change phone number - OTP send on updated mobile number and phone number change successfully | 1) Loged In 2) Click on Setting 3) My Profile 4) Profile 5) Click on Update 6) Enter new phone number 3) Update |  | A mail/message with 6 digit verification code is sent successfully. Phone number changed successfully. |  | Pass |  |  |  |  | OTP sent on email address not on phone
|  | Verify Phone number |  |  |  | It should be allowed more than 10 digits for other country. For India it should be allowed 10 digits phone number | Fail | [5 empty] | Done
|  | Verify when we update the DOB, Password should be updated by user name along with @ + DOB's year | dh@yopmail.com Doctor@2002 |  | Old DOB 03/12/2000 I have updated DOB like DOB - 03/12/2002 So, my credential should be Doctor@2002 | 1) My previous DOB was 03/12/2000 so password is Doctor@2000 I have updated DOB like DOB - 03/12/2002 My new password should be Doctor@2002 But here I got message like "Invalid password" Pls refer video | Fail | [5 empty] | Password can be changed by change password or forogot password only directely it can not be changed
| Edit Change Password | Verify title like Profile/Change Password/Manage Notification/2FA/Deactivate Account |  |  |  |  | Pass
|  | Verify title like Current Password/Password/Confirm Password |  |  | It should be as below : Current Password New Password Confirm Password | Titles come as below : Current Password Password Confirm Password | Fail | [5 empty] | Done
|  | Verify current password and New password both are different when we update password | 1) LoggedIn 2) My Profile 3) Change Password 4) Enter current password, New password, confirm Password 5) Update |  |  |  | Pass
|  | Verify validation message of current password |  |  | "Current password is required" | As per expected result | Pass
|  | Verify validation message of Password |  |  | It should be "New Password is required" | Password is required | Fail | [5 empty] | Done
|  | Verify validation message of Confirm password |  |  | "Confirm Password is required" | As per expected result | Pass
|  | Verify - When we enter new Password and confirm password different, then check validation msg |  |  | It should be "Confirm Password does not match" | Confirm Passwords does not match | Fail | [5 empty] | Done
|  | Verify when we enter wrong current password it will not allow to be entered |  |  | Invalid old password. | Message should be "Invalid current password". | Pass
| Manage Notification | Verify functionality of below : Push Notification Email Notification Message Notification |  |  |  |  | Remaining
|  | Validation message for Push/Email/Message notification |  |  | Push notification turned off successfully. Push notification turned on successfully. Email notification turned off successfully. Email notification turned on successfully. Message notification turned off successfully Message notification turned on successfully. | Same as expected result | Pass |  |  |  |  | Functionality remaining
| 2FA | [5 empty] | Remaining
| Deactivate | Verfiy Two fector authentification on/off |  |  | Two-factor authentication turned on successfully. Two-factor authentication turned off successfully. | Same as expected result | Remaining
| Delete Account | Verify delete acc functionality
|  | Why User Id in general details comes like 670917b67b0175da4511e1f |  |  |  |  | Fail
d

## Company
DATE OF CREATION | 30.09.24 |  |  |  |  | TOTAL PASS | 1
MODULE NAME | Setting-Company |  |  |  |  | TOTAL FAIL | 7
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 8
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
30.09.24 | Company Management | Verify path |  |  | It should be Dashboard / Setting / Company | Path is as like : Dashboard / Company | Pass |  |  |  | there isn't setting module/path | No need to do
|  | Verify image upload |  |  | JPEG should also be allowed | Only Accepts .png and .svg files only. | Pass |  |  |  | only png and svg are compatible | No need to do
|  | Verify title like Organizations : Organzation details Name/App Name Organzation Address : Line one/Line Two/Pincode/City/State/ Country/Time Zone/Language/Currency/ Date Format/Time Format/Week Start Day/ Social Links Maintenance Details |  |  | It should be as below : Organzation details: Name App Name Organization Address : Address Line 1 Address Line 2 Pincode City State Country Time Zone Language Currency Date Format Time Format Week Start Day Social Links Maintenance Details | Verify titles like Organizations : Organzation details: Name App Name Organzation Address : Line one Line Two Pincode City State Country Time Zone Language Currency Date Format Time Format Week Start Day Social Links Maintenance Details | Pass |  |  |  | done | Done 18.10.24
|  | Verify validation message |  |  | It should be as below : Orgnaization Name : "Organization name is required" Address Line 1 - "Address Line 1 is required" Address Line 2 - "Address Line 2 is required" Pincode - Pincode is required | It displays like below : Orgnaization Name : "organization name is required" Address Line 1 : "line one is required" Address Line 2 : NA Pincode : Pincode is required | Pass |  |  |  | address line 2 is optional | Done 18.10.24
|  | Verify pincode digit |  |  | It should be six digits. | Same as expected result | Pass |  |  |  |  | Done 18.10.24
|  | Verify characters and special characters should not be allowed |  |  |  |  | Pass
|  | Verify short decription coming before the Organization country |  |  | Country Flag should be came before Country name |  | Pass |  |  |  |  | Done 18.10.24
|  | Verify validation message of successful updation in company -->setting |  |  | Validation message should be as below : "Setting details updated successfully." | Here, message comes like below which is gramatically incorrect. "Setting details updated get successfully." | Fail |  |  |  |  | Backend
| Maintenance | Verify Maintenance functionality working well |  |  |  |  | Remaining
d

## Address
DATE OF CREATION | 30.09.24 & 01.10.24 |  |  |  |  | TOTAL PASS | 5
MODULE NAME | Setting-Address |  |  |  |  | TOTAL FAIL | 11
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 16
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
11.10.24 | Address | Verify Path |  |  | Path should be Dashboard / Setting / address | Path comes like : Dashboard / address | Pass |  |  |  | there isn't any setting module | Done 18.10.24
| Add Address | Verify title |  |  | It should be as below : Name Phone Address Line 1 Address Line 2 Pincode City State Country | Titles come like below : Name Phone Line one Line Two Pincode City State Country | Pass |  |  |  | done | Done 18.10.24
|  | Verify validation messages |  |  | It should be as below : Name-Name is required Phone-Phone number is required Line One-Address Line 1 is required Line Two-Address Line 2 is required Pincode-Pincode is required | It comes as below: Name-Name is required Phone-Phone number is required Line One-Line one is required Line Two-NA Pincode-Pincode is required | Pass |  |  |  | done | Done 18.10.24
|  | Verify phone number, short description comes with country code inplace of flag icon |  |  | Flag should be came |  | Fail |  |  |  |  | Done 18.10.24
|  | Verify max value of address line 1 & 2 |  |  |  | Max value set 80 characters Here, max value set by 80 character and validation message comes like as below : The address line one may not be greater than 50 characters. Please Set any one value i.e 80 character max in address line 1 and 2 | Pass |  |  |  | done | Done 18.10.24
|  | Verify First letter should be capital in Name / Address Line 1 / Address Line 2 |  |  |  |  | Pass |  |  |  | done | Done 18.10.24
|  | Verify phone number |  |  |  | When we enter more than 10 digits phone number then it should be allowed for other country. For India we can set validation for allowing 10 digits in phone number | Pass |  |  |  | done | Done 18.10.24
| Back | Verify back button functionality |  |  |  |  | Pass
| Edit address button functionality | Verify edit button functionality | 1) Logged In 2) Click on Settings 3) Click on Address 4) Click on edit button 5) Click on Edit 6) Update details 7) Click on Update button |  |  |  | Pass
|  | Verify max limit of characters in name |  |  |  | Validation message comes like "The name may not be greater than 50 characters." Here it is allow to enter more than 50 characters however data is not save. But strict validation shoud be there not allowing to enter more than 50 characters Pls do the same in the address1/2 too. | Pass |  |  |  | done | Done 18.10.24
|  | UI of Address |  |  | It should be arrange same as below: Name Address Line 1 Address Line 2 City-Pin, State, Country. Phone ……………………………………………. Address should be as per below format : Ronak Xczxc, Zxczxc, Mehsana - 856856, Gujarat, India. +91 9427604051 | Ronak Xczxc, Zxczxc, Mehsana - 856856, Gujarat, India. +919427604051 | Pass |  |  |  | done | "Done 18.10.24"
|  | Verify address Format - It should be fixed |  |  | When we enter long characters name format should be fixed and name should be came in second line or display .. Like : Zxczxc…. For below name Zxczxchhhhhhhhhhhhhhhhhhhhhhhhhhhhhhh | Here, name comes in one line and format has been changed. Please refer poonam coatings Bank details module in company management | Fail |  |  |  | done | Not Done Will do later
|  | When we update wrong pincode |  |  | Data not found. | Data not found. | Pass
|  | Verify edit address line 1 & 2 Max character should be set with 80 characters |  |  |  | Here, max value set by 80 characters and validation message comes like as below : The address line one may not be greater than 50 characters. The address line two may not be greater than 50 characters. Please Set any one value i.e 80 character max in address line 1 and 2 in edit of address | Pass |  |  |  | max char is 50 | Done 18.10.24
| Delete button functionality | Verify delete button functionality | 1) Loged In 2) Click on Setting 3) Click on Address 4) Click on Delete button which you want to delete 5) Click on "Yes,Delete" |  | Address deleted successfully. | As per expected result | Pass
| Cancel button functionality | Verify cancel button functionality work |  |  |  |  | Pass
d

## User
DATE OF CREATION | 01.10.24 |  |  |  | TOTAL PASS | 25
MODULE NAME | Setting-User |  |  |  | TOTAL FAIL | 14
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 39
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Design Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
User-Administrator | Verify Path |  |  | It should be Dashboard/User/ / Administrator Directory | Dashboard / Administrator directory | Fail | [5 empty] | breadcrumb updated
| Please update the name "Administrators Directory" with "Administrator Details" or "Administrator Insights" |  |  |  |  | Fail | [5 empty] | Insights
| Verify title like Name/Contact Info/Status/Gender/Last Login/Created at/Action |  |  |  |  | Pass
| Verify filter of gender like All/Male/Female |  |  |  |  | Pass
| Verify sort filter newest / Oldest functionality |  |  |  |  | Pass
| One option should be added like "All" If possible All Oldest Newest |  |  | All Oldest Newest | Oldest Newest | Fail | [5 empty] | it doesn't work with all
| Verify search button functionality |  | Hariprasad |  |  | Pass
Add User | Gender / Sort UI - Please keep same UI for all |  |  |  | Here UI is different than other | Fail | [5 empty] | Done
| Verify title like First Name/Last Name/Email/Phone Number/Gender/Date of Birth/Privileges |  |  |  |  | Pass
| In Gender - there are two option like : Male Female Other should be there pls add it |  |  |  |  | Fail | [5 empty] | Done
| Verify validation message at the time of entering min characters in First name |  |  | It should be as below : "First Name must be at least 3 characters long" | Validation message comes like : Name must be at least 3 characters long | Fail | [5 empty] | Done
| Verify validation message at the tim of entering min characters in Last name |  |  | Last Name must be at least 3 characters long | Same as Expected result | Pass
| Verify validation message of email/ Phone/Gender |  |  | Validation message should be came | Email address should not be empty Phone number is required Gender is required | Pass
| Verify validation message for entering max characters in Fname and Lname |  |  | First name must be less than 50 characters Last name must be less than 50 characters 50 characters max is enough and we have aleady set in Application use too | First name must be less then 80 characters Last name must be less then 80 characters | Pass
| Verify phone number digits |  |  |  |  | Pass
| Verify phone number, short description comes with country code inplace of flag icon |  |  | Flag should be came |  | Fail
| Verify date format |  |  | It should be as below dd/mm/yyyy | Here it is allowed 6 digits it is dd/mm/yyyyyy allowed 03/04/200990 | Fail
View button functionality | Verify view button functionality | 1) Logged In 2) Click on User Management 3) Click on Address 4) Click on view icon that you want to view |  |  |  | Pass
| When we lick on view the url comes as below : https://admin.peak72finance.com/administrator-directory/670765818df1d6cbffb38e8d |  |  | It should be : https://admin.peak72finance.com/administrator-directory/View or else |  | Fail | [5 empty] | https://admin.peak72finance.com/administrator-directory/670765818df1d6cbffb38e8d here 670765818df1d6cbffb38e8d id is required in url thats unique
Edit button functionality | Verify edit button functionality | 1) Logged In 2) Click on User Management 3) Click on View 4) Click on update 5) update information that u want to update 6) Click on Submit |  | User details updated successfully. |  | Pass
| Verify privileges read/write/delete/all |  |  |  |  | Pass
Back button Functionality | Verify abort button functionality |  |  |  |  | Pass
Deactivate button functionality | Verify deactivate/Activate user button functionality | 1) Logged In 2) Click on User Management 3) Click on Action button 5) Submit |  | Activate the User? Are you sure want to Activate the user? User state changed |  | Pass
Delete button functionality | Verify delete button functionality |  |  | User removed successfully | As per expected in result | Pass
| Verify duplicate email and phone number not allowed to be entered |  |  | This phone number already taken. This email address already taken. |  | Pass
| Verify privileges work on user |  |  |  |  | Remaining
User-ApplicationUser | Verify UI of Gender and sort |  |  |  |  | Pass
| Verify title like Name/Contact Info/Status/Gender/Last Login/Created at/Action |  |  |  |  | Pass
| There is column for Gender but data not comes, It is blanked |  |  |  |  | Fail | [5 empty] | initially app user not selecting user
| Max characters limit is 50 characters in first name/last Name |  |  |  |  | Pass
Image Upload | Verify dummy text coming like "Joined NaN undefined, NaN" |  |  |  |  | Fail | [5 empty] | removed
View button functionality | Verify view button functionality |  |  |  |  | Pass
| When we click on view ul comes as below : https://admin.peak72finance.com/application-users/66fe23268df1d6cbffb378e3 |  |  | It should be : https://admin.peak72finance.com/application-users/view or else |  | Fail | [5 empty] | id is required thats unique
Deactivate user | Verify functionality of deactivate user |  |  |  | When I deactivated user one message coming like "Couldn't parse the specified URI." | Fail | [5 empty] | done
Edit Application User | Edit App User functionality |  |  |  | Not available | Pass
Delete button functionality | Verify delete button functionality |  |  | User removed successfully |  | Pass
Select all | Verify after click on select all item and delete all, all selected record should be deleted | 1) Logged In 2) Click On User 3) Click on Application User 4) Click on select all button 5) Click on "Delete All3" button 6) Click on "Yes Delete" button |  | User removed successfully | Pages removed successfully | Fail | [5 empty] | done
| Verify "No, Cancel" button work |  |  |  |  | Pass
Rows Filter | Verify filter of the row i.e 6/12/18…… |  |  | Data display as per selection of row | Data displays correctly | Pass
| Verify text comes like "Showing 1 to 6 of 7 entries". It should be vary as per the selection of rows |  |  | "Showing 1 to 6 of 7 entries" |  | Pass
Page Filter | Verify the page filter Check previous and next button work |  |  |  | Its working well | Pass
d